## costSummary
Project Name:		Sampleclient New Residence		JOB NO:	5001
Client:		M/M Joe Sampleclient		SF FIN	3200
Architect:		Handy Sketcher		SF UNFIN	1600
Location:		12345 Market St, Anytown, ID 83800		SF TOTAL	4800
	Class	Class Name	Cost		Cost/sf
	00 00 00	PROCUREMENT AND CONTRACTING REQ	2450.00		0.51
	01 00 00	GENERAL REQUIRMENTS	29886.00		6.23
	02 00 00	EXISTING CONDITIONS	1150.00		0.24
	03 00 00	CONCRETE	27860.00		5.80
	04 00 00	MASONRY	7040.00		1.47
	05 00 00	METALS	450.00		0.09
	06 00 00	WOOD, PLASTICS AND COMPOSITES	85710.60		17.86
	07 00 00	THERMAL AND MOISTURE PROTECTION	37610.00		7.84
	08 00 00	OPENINGS	16780.00		3.50
	09 00 00	FINISHES	51316.25		10.69
	10 00 00	SPECIALTIES	6528.00		1.36
	11 00 00	EQUIPMENT	9225.00		1.92
	12 00 00	FURNISHINGS	24528.00		5.11
	13 00 00	SPECIAL CONSTRUCTION	2892.00		0.60
	14 00 00	CONVEYING EQUIPMENT	5722.00		1.19
	21 00 00	FIRE SUPPRESSION	0.00		0.00
	22 00 00	PLUMBING	13150.00		2.74
	23 00 00	HVAC	9007.00		1.88
	25 00 00	INTEGRATED AUTOMATION	0.00		0.00
	26 00 00	ELECTRICAL	14804.00		3.08
	27 00 00	COMMUNICATIONS	1800.00		0.38
	28 00 00	ELECTRONIC SAFETY AND SECURITY	0.00		0.00
	31 00 00	EARTHWORK	12915.00		2.69
	32 00 00	EXTERIOR IMPROVEMENTS	45233.00		9.42
	33 00 00	UTILITIES	11275.00		2.35
	35 00 00	WATERWAY AND MARINE CONSTRUCTION	0.00		0.00
		SUBTOTAL	417331.85		86.94
		SALES TAXES	25039.91	6.0%	5.22
		CONTINGENCY, OVERHEAD & PROFIT	62599.78	15%	13.04
		TOTAL QUOTE	504971.54		105.20

		ADDITIONAL CONSIDERATIONS FOR SPECULATION PROJECTS
		LAND	162500.00
		LOAN FEES	10000.00
		INTEREST CHARGES	28000.00
		CLOSING COSTS	8200.00
		SELLING COMMISSIONS	51000.00
		MARKETING COSTS	22000.00
		SUBTOTAL SPEC COSTS	281700.00
		ADDITIONAL COP MARKUP	42255.00	15%
		TOTAL SALES PRICE	828926.54

## residentialDrawSheet
COST BREAKDOWN REPORT / DRAW SHEET				Sampleclient New Residence

1	Arch/Eng/Assess/Mitig/Temp	31036.00	35691.40		7.437%
2	Permits & procurement	2450.00	2817.50		0.587%
3	Excavation & earthwork	12915.00	14852.25		3.095%
4	Utilities & drainage	11275.00	12966.25		2.702%
5	Concrete - structural	20660.00	23759.00		4.950%
6	Damproofing - water repellents	380.00	437.00		0.091%
7	Framing - decks - porches	70127.00	80646.05		16.804%
8	Roofing	12100.00	13915.00		2.899%
9	Exterior windows & doors	9650.00	11097.50		2.312%
10	Plumbing rough 75%	9862.50	11341.88		2.363%
11	Electrical rough 75%	12453.00	14320.95		2.984%
12	Siding - soffit - cladding	18600.00	21390.00		4.457%
13	Masonry & stone	7040.00	8096.00		1.687%
14	Concrete finishing	7200.00	8280.00		1.725%
15	HVAC	9007.00	10358.05		2.158%
16	Insulation	6380.00	7337.00		1.529%
17	Fire suppression & barriers	150.00	172.50		0.036%
18	Drywall & wall finish	21731.25	24990.94		5.207%
19	Painting & finishes	8683.00	9985.45		2.081%
20	Ceiling systems	0.00	0.00		0.000%
21	Tiling & stone	7100.00	8165.00		1.701%
22	Flooring	13802.00	15872.30		3.307%
23	Interior doors & trim	23163.60	26638.14		5.550%
24	Cabinets & furnishings	24528.00	28207.20		5.877%
25	Specialties	6528.00	7507.20		1.564%
26	Equipment & conveyance	14947.00	17189.05		3.582%
27	Plumbing finish 25%	3287.50	3780.63		0.788%
28	Electric finish 25%	4151.00	4773.65		0.995%
29	Landscape & exterior	45233.00	52017.95		10.839%
30	Special & outbuildings	2892.00	3325.80		0.693%
31	Waterway & marine	0.00	0.00		0.000%
32	Subtotal Hard Costs:	417331.85	479931.63		100.000%
33	Profit & contingency	62599.78
34	Sales Tax	25039.91	25039.91
35	Loan fees & interest	38000.00
36	Land costs	162500.00
37	Markup Land & loan	42255.00
38	Closing & commissions	81200.00
39	TOTAL COSTS:	828926.54	504971.54

## dataTakeOffs
CLASS	CLASS TITLE	DESCRIPTION	UNIT	QUANT	RATE	EXTEND
00 00 00	PROCUREMENT AND CONTRACTING REQ	2450.00				0.00
00 11 19	request for proposal					0.00
00 11 53	request for qualifications					0.00
00 25 13	pre-bid meetings	no charge				0.00
00 25 16	pre-proposal meetings	no charge				0.00
00 31 43	permit application	Kootenai County	ea	1	200	200.00
00 31 46	permits - mitigations - fees	Kootenai County	ea	1	2250	2250.00
00 41 00	bid forms					0.00
00 60 00	project forms					0.00
00 61 00	bond forms					0.00
00 62 00	certificates and other forms					0.00
						0.00
01 00 00	GENERAL REQUIRMENTS	29886.00				0.00
01 10 00	summary					0.00
01 31 00	project management and coordination	in house	hours	320	52	16640.00
01 31 13	project coordination					0.00
01 31 14	facility services coordination		hours	4	52	208.00
01 31 19	project meetings		hours	16	52	832.00
01 31 23	project website	add-on to company site	ea	1	300	300.00
01 31 26	electronic communication protocols	cell phones	mo	4	120	480.00
01 32 00	construction progress documentation		hours	16	52	832.00
01 32 13	scheduling of work		hours	32	52	1664.00
01 32 16	construction progress schedule	no charge				0.00
01 32 19	submittals schedule	no charge				0.00
01 32 23	survey and layout data	client				0.00
01 32 26	construction progress reporting	no charge				0.00
01 32 33	photographic documentation	no charge				0.00
01 32 43	purchase order tracking					0.00
01 33 00	submittal procedures					0.00
01 35 00	special procedures					0.00
01 35 23	owner safety procedures	safety manual for jobsite	manual	1	220	220.00
01 35 43	environmental procedures					0.00
01 35 46	indoor air quality					0.00
01 35 53	security procedures	client				0.00
01 40 00	quality requirements					0.00
01 41 00	regulatory requirements					0.00
01 42 00	references	client spec sheets				0.00
01 43 00	quality assurance					0.00
01 43 36	field samples					0.00
01 43 39	mockups					0.00
01 45 00	quality control					0.00
01 46 23	testing and inspection services	concrete	ea	3	60	180.00
01 50 00	temporary facilities and controls					0.00
01 51 00	temporary utilities	client				0.00
01 51 13	temporary electricity	client				0.00
01 51 19	temporary fuel oil		gal	120	3	360.00
01 51 23	temporary hvac	heater rental - 2 x 1 mo	mo	2	220	440.00
01 51 26	temporary lighting					0.00
01 51 33	temporary telecommunications					0.00
01 51 36	temporary water	client				0.00
01 52 00	construction facilities					0.00
01 52 13	field offices and sheds	shack - 4 mo + move	mo	5	120	600.00
01 52 16	first aid facilities	kits	ea	1	55	55.00
01 52 19	sanitary facilities	toilet - 4 mo + move	mo	5	75	375.00
01 53 00	temporary construction					0.00
01 54 00	construction aids					0.00
01 54 16	temporary hoists					0.00
01 54 19	temporary cranes	trusses	hours	4	120	480.00
01 54 23	temporary scaffolding and platforms					0.00
01 55 00	vehicular access and parking					0.00
01 56 00	temporary barriers and enclosures					0.00
01 56 23	temporary barricades					0.00
01 56 26	temporary fencing					0.00
01 56 39	temporary tree and plant protection					0.00
01 57 00	temporary controls					0.00
01 57 13	temporary erosion and sediment control	silt fence	lf	300	3	900.00
01 57 16	temporary pest control					0.00
01 57 19	temporary enviropnmental controls					0.00
01 57 23	temporary storm water pollution control					0.00
01 60 00	product requirements					0.00
01 70 00	execution and closeout requirements					0.00
01 71 13	mobilization					0.00
01 71 23	field engineering					0.00
01 71 33	protection of adjacent construction					0.00
01 73 00	execution					0.00
01 74 00	cleaning and waste management					0.00
01 74 13	progress cleaning					0.00
01 74 16	site maintenance	in house	hours	120	35	4200.00
01 74 19	construction waste management and disposal	dump fees	tons	15	32	480.00
01 74 23	final cleaning		bid	1	500	500.00
01 75 00	starting and adjusting					0.00
01 76 00	protecting installed construction					0.00
01 77 00	closeout procedures	no charge				0.00
01 93 13	facility maintenance procedures	manual	hours	4	35	140.00
						0.00
02 00 00	EXISTING CONDITIONS	1150.00				0.00
02 01 00	maintenance of existing conditions					0.00
02 01 50	maintenance of site remediation					0.00
02 05 00	common work results for existing conditions					0.00
02 05 19	geosynthetics for existing conditions					0.00
02 06 00	schedules for existing conditions					0.00
02 21 00	surveys					0.00
02 22 00	existing conditions assessment					0.00
02 24 00	environmental assessment	phase 1	ea	1	250	250.00
02 25 00	existing material assessment					0.00
02 26 00	hazardous material assessment		bid	1	250	250.00
02 31 00	geophysical investigations					0.00
02 32 00	geotechnical investigations		bid	1	650	650.00
02 41 13	selective site demolition					0.00
02 41 16	structure demolition					0.00
02 42 00	removal and salvage of construction materials					0.00
02 43 00	structure moving					0.00
02 50 00	site remediation					0.00
02 60 00	contaminated site material removal					0.00
02 70 00	water remediation					0.00
02 80 00	facility remediation					0.00
						0.00
03 00 00	CONCRETE	27860.00				0.00
03 11 00	concrete forming		bid	1	12500	12500.00
03 11 19	insulating concrete forming					0.00
03 15 00	concrete accessories	included in forming bid				0.00
03 16 00	concrete anchors		lump	1	500	500.00
03 21 00	reinforcing steel	included in forming bid				0.00
03 22 00	welded wire fabric reinforcing					0.00
03 24 00	fibrous reinforcing					0.00
03 25 00	composite reinforcing					0.00
03 30 00	cast-in-place concrete					0.00
03 31 00	structural concrete		cy	56	110	6160.00
03 31 16	lightweight structural concrete					0.00
03 31 23	high-performance structural concrete					0.00
03 33 00	architectural concrete					0.00
03 35 00	concrete finishing	m/l	sf	1600	4.5	7200.00
03 37 00	specially placed concrete					0.00
03 37 16	concrete pumps		trips	3	500	1500.00
03 38 00	post-tensioned concrete					0.00
03 39 00	concrete curing					0.00
03 40 00	precast concrete					0.00
03 47 00	site-cast concrete					0.00
03 47 13	tilt-up concrete					0.00
03 48 00	precast concrete specialties					0.00
03 50 00	cast decks and underlayment					0.00
03 60 00	grouting					0.00
03 70 00	mass concrete					0.00
03 80 00	concrete cutting and boring					0.00
						0.00
04 00 00	MASONRY	7040.00				0.00
04 20 00	unit masonry					0.00
04 22 00	concrete unit masonry					0.00
04 23 00	glass unit masonry					0.00
04 24 00	adobe unit masonry					0.00
04 25 00	unit masonry panels					0.00
04 26 00	single-wythe unit masonry					0.00
04 27 00	multiple-wythe unit masonry					0.00
04 43 00	stone masonry					0.00
04 50 00	refractory masonry					0.00
04 57 00	masonry fireplaces					0.00
04 57 33	modular masonry fireplaces					0.00
04 73 00	manufactured stone masonry	m/l	sf	320	22	7040.00
						0.00
05 00 00	METALS	450.00				0.00
05 05 23	metal fastenings					0.00
05 12 00	structural steel framing					0.00
05 20 00	metal joists					0.00
05 21 00	steel joists framing					0.00
05 40 00	cold-formed metal framing					0.00
05 41 00	structural metal stud framing					0.00
05 42 00	cold-formed metal joist framing					0.00
05 50 00	metal fabrications					0.00
05 70 00	decorative metal	porch stair rail	ea	1	450	450.00
						0.00
06 00 00	WOOD, PLASTICS AND COMPOSITES	85710.60				0.00
06 05 23	wood, plastic and composite fastenings		lump	1	1000	1000.00
06 05 73	wood treatments					0.00
06 05 83	shop-applied wood coatings					0.00
06 10 00	rough carpentry		bid	1	22670	22670.00
06 11 00	wood framing	see lumber take-off	quote	1	38522	38522.00
06 12 00	structural panels					0.00
06 15 00	wood decking	included in lumber take-off and labor bid				0.00
06 16 00	sheathing	see lumber take-off				0.00
06 16 13	insulating sheathing					0.00
06 16 23	subflooring	see lumber take-off				0.00
06 16 26	underlayment					0.00
06 16 43	gypsum sheathing					0.00
06 16 63	cementitious sheathing					0.00
06 17 13	laminated veneer lumber					0.00
06 17 23	parallel strand lumber					0.00
06 17 25	laminated strand lumber					0.00
06 17 27	oriented strand lumber					0.00
06 17 33	wood i-joists	see lumber take-off				0.00
06 17 36	metal-web wood joists					0.00
06 17 43	rim boards	see lumber take-off				0.00
06 17 53	shop-fabricated wood trusses		quote	1	7485	7485.00
06 18 13	glued-laminated beams	see lumber take-off				0.00
06 20 23	interior finish carpentry	labor	bid	1	4250	4250.00
06 22 13	standard pattern wood trim					0.00
06 25 00	prefinished panelling		quote	320	4	1280.00
06 26 00	board panelling					0.00
06 42 00	wood panelling					0.00
06 42 16	wood-veneer panelling					0.00
06 42 19	plastic-laminate-faced wood panelling					0.00
06 42 99	interior handrails					0.00
06 43 00	wood stairs and railings	m/l	quote	1	3277	3277.00
06 44 13	wood turnings					0.00
06 44 16	wood pilasters					0.00
06 44 19	wood grilles					0.00
06 44 23	wood corbels					0.00
06 44 26	wood cupolas					0.00
06 44 29	wood finials					0.00
06 44 33	wood mantels		ea	1	680	680.00
06 44 36	wood pediment heads					0.00
06 44 39	wood posts and columns	m/l	ea	5	185	925.00
06 46 13	wood door and window casings		lf	600	1.52	912.00
06 46 16	wood aprons		lf	144	2.15	309.60
06 46 19	wood base and shoe moldings		lf	1200	1.35	1620.00
06 46 23	wood chair rails		lf	120	1.85	222.00
06 46 26	wood cornices	m/l	lf	280	6.5	1820.00
06 46 99	wood crown		lf	120	6.15	738.00
06 50 00	structural plastics					0.00
06 51 13	plastic lumber					0.00
06 53 00	plastic decking					0.00
06 63 00	plastic railings					0.00
06 66 00	custom ornamental simulated woodwork					0.00
06 71 13	composite lumber					0.00
06 72 13	composite joist assemblies					0.00
06 73 13	composite structural decking					0.00
06 81 00	composite railings					0.00
06 83 00	composite panelling					0.00
						0.00
07 00 00	THERMAL AND MOISTURE PROTECTION	37610.00				0.00
07 11 00	damproofing					0.00
07 13 00	sheet waterproofing					0.00
07 14 00	fluid-applied waterproofing		bid	1	380	380.00
07 19 00	water repellents					0.00
07 21 00	thermal insulation					0.00
07 21 13	board insulation	m/l	sf	320	2	640.00
07 21 16	blanket insulation	wall - floor - plug	bid	1	5500	5500.00
07 21 19	foamed-in-place insulation					0.00
07 21 23	loose-fill insulation					0.00
07 21 26	blown insulation		bid			0.00
07 21 99	visqueen	slab	sf	2000	0.12	240.00
07 22 00	roof and deck insulation					0.00
07 30 05	roof felt and underlayment					0.00
07 31 00	shingles and shakes					0.00
07 31 13	asphalt shingles	incl ridge - vents - jacks	bid	1	9450	9450.00
07 31 16	metal shingles					0.00
07 31 19	mineral-fiber cement shingles					0.00
07 31 29	wood shingles and shakes					0.00
07 31 33	composite rubber shingles					0.00
07 31 53	plastic shakes					0.00
07 32 13	clay roof tiles					0.00
07 32 16	concrete roof tiles					0.00
07 32 19	metal roof tiles					0.00
07 32 26	plastic roof tiles					0.00
07 41 00	roof panels					0.00
07 41 13	metal roof panels					0.00
07 41 43	composite roof panels					0.00
07 42 13	metal wall panels					0.00
07 42 43	composite wall panels					0.00
07 44 00	faced panels					0.00
07 46 23	wood siding					0.00
07 46 26	hardboard siding	side - soffit - vents	bid	1	18600	18600.00
07 46 33	plastic siding					0.00
07 46 46	fiber-cement siding					0.00
07 52 00	modified bituminous sheet roofing					0.00
07 53 00	elastomeric membrane roofing					0.00
07 54 00	thermoplastic membrane roofing					0.00
07 56 00	fluid-applied roofing					0.00
07 57 00	coated foam roofing					0.00
07 58 00	roll roofing					0.00
07 61 00	sheet metal roofing					0.00
07 62 00	sheet metal flashing and trim					0.00
07 71 23	manufactured gutters and downspouts		bid	1	2650	2650.00
07 72 26	ridge vents					0.00
07 72 27	eave vents					0.00
07 72 29	roof exhaust vents					0.00
07 72 36	smoke vents					0.00
07 77 00	wall specialties					0.00
07 81 00	applied fireproofing					0.00
07 81 33	mineral-fiber fireproofing					0.00
07 84 00	firestopping	garage caulking	limp	1	150	150.00
07 87 00	smoke containment barriers					0.00
						0.00
08 00 00	OPENINGS	16780.00				0.00
08 11 00	metal doors and frames					0.00
08 14 13	carved wood doors					0.00
08 14 16	flush wood doors					0.00
08 14 23	clad wood doors					0.00
08 14 29	prefinished wood doors		ea	22	185	4070.00
08 14 33	stile and rail doors					0.00
08 14 73	sliding wood doors					0.00
08 14 76	bifolding wood doors		pr	8	150	1200.00
08 15 00	plastic doors					0.00
08 16 00	composite doors					0.00
08 16 13	fiberglass doors					0.00
08 16 73	sliding composite doors					0.00
08 16 76	bifolding composite doors					0.00
08 17 00	integrated door opening assemblies					0.00
08 30 00	specialty doors and frames					0.00
08 31 13	access doors and frames		ea	2	180	360.00
08 31 16	access panels and frames					0.00
08 32 00	sliding glass doors		ea	2	265	530.00
08 33 23	overhead coiling doors		bid	1	1250	1250.00
08 34 00	special function doors					0.00
08 35 00	folding doors and grilles					0.00
08 38 00	traffic doors					0.00
08 41 00	entrances and storefronts	see list	lump	1	2200	2200.00
08 44 33	sloped glazing assemblies					0.00
08 50 00	windows		quote	1	6200	6200.00
08 50 66	window screens	included				0.00
08 56 00	special function windows					0.00
08 60 00	roof windows and skylights					0.00
08 71 00	door hardware		lump	1	650	650.00
08 74 00	access control hardware					0.00
08 79 00	hardware accessories					0.00
08 79 13	key storage equipment					0.00
08 81 13	decorative glass glazing					0.00
08 83 00	mirrors	m/l	bid	1	320	320.00
						0.00
09 00 00	FINISHES	51316.25				0.00
09 21 13	plaster assemblies					0.00
09 21 16	gypsum board assemblies		sf	17385	1.25	21731.25
09 21 16.23	gypsum board shaft wall assemblies					0.00
09 21 16.33	gypsum board area separation wall assemblies					0.00
09 22 13	metal furring					0.00
09 22 16	non-structural metal framing					0.00
09 22 26	suspension systems					0.00
09 22 36	lath					0.00
09 25 00	other plastering					0.00
09 30 13	ceramic tiling	incl laid-in shower pan & hardi	bid	1	6250	6250.00
09 30 16	quarry tiling					0.00
09 30 19	paver tiling					0.00
09 30 23	glass mosaic tiling					0.00
09 30 26	plastic tiling					0.00
09 30 29	metal tiling					0.00
09 30 33	stone tiling	incl hardi - entry	bid	1	850	850.00
09 30 36	concrete tiling					0.00
09 30 39	brick tiling					0.00
09 31 00	thin-set tiling					0.00
09 32 00	mortar-bed tiling	incl shower bid				0.00
09 33 00	conductive tiling					0.00
09 34 00	waterproofing-membrane tiling					0.00
09 51 00	acoustic ceilings					0.00
09 53 00	acoustical ceiling suspension assemblies					0.00
09 54 00	specialty ceilings					0.00
09 57 00	special function ceilings					0.00
09 61 13	acoustic underlayment					0.00
09 61 00	flooring treatment					0.00
09 62 12	asphaltic plank flooring					0.00
09 62 19	laminate flooring		bid	1	3226	3226.00
09 62 23	bamboo flooring					0.00
09 62 29	cork flooring					0.00
09 63 00	masonry flooring					0.00
09 64 00	wood flooring					0.00
09 65 00	resilient flooring		bid	1	1800	1800.00
09 66 00	terrazzo flooring					0.00
09 67 00	fluid-applied flooring					0.00
09 68 00	carpeting		bid	1	8776	8776.00
09 70 00	wall finishes					0.00
09 72 00	wall coverings					0.00
09 75 00	stone facing	frpl m/l	bid	1	320	320.00
09 77 00	special wall surfacing					0.00
09 80 00	acoustic treatment					0.00
09 84 00	acoustic room components					0.00
09 91 13	exterior painting		bid	1	3299	3299.00
09 91 23	interior painting		bid	1	4222	4222.00
09 93 13	exterior staining and finishing					0.00
09 93 23	interior staining and finishing		bid	1	520	520.00
09 94 13	textured finishing					0.00
09 94 16	faux finishing		bid	1	322	322.00
09 94 19	multicolor interior finishing					0.00
09 96 00	high-performance coatings					0.00
09 97 00	special coatings					0.00
						0.00
10 00 00	SPECIALTIES	6528.00				0.00
10 11 00	visual display units					0.00
10 12 00	display cases					0.00
10 14 00	signage & street numbers	m/l	lump	1	150	150.00
10 21 13	toilet compartments					0.00
10 21 16	shower & dressing compartments					0.00
10 22 19	demountable partitions					0.00
10 22 33	accordian folding partitions					0.00
10 26 00	wall and door protection					0.00
10 26 13	corner guards					0.00
10 26 19	bumper guards					0.00
10 28 13	toilet accessories		lump	1	200	200.00
10 28 16	bath accessories		lump	1	200	200.00
10 28 19	tub and shower doors		bid	1	320	320.00
10 28 23	laundry accessories					0.00
10 28 99	grab bars					0.00
10 31 00	manufactured fireplaces	m/l	bid	1	3850	3850.00
10 32 19	fireplace screens					0.00
10 32 23	fireplace doors					0.00
10 35 00	stoves					0.00
10 41 00	emergency access and information cabinets					0.00
10 43 00	emergency aid specialties					0.00
10 44 00	fire protection specialties					0.00
10 50 00	storage specialties					0.00
10 51 00	lockers					0.00
10 55 00	postal specialties		lump	1	200	200.00
10 56 13	metal storage shelving					0.00
10 56 16	fabricated wood storage shelving					0.00
10 56 17	wall-mounted standards and shelving					0.00
10 56 23	wire storage shelving					0.00
10 56 29	storage racks					0.00
10 57 13	hat and coat racks					0.00
10 57 23	closet and utility shelving		bid	1	1228	1228.00
10 70 00	exterior specialties					0.00
10 71 16	storm panels					0.00
10 73 13	awnings					0.00
10 73 16	canopies					0.00
10 73 23	car shelters					0.00
10 73 26	walkway coverings					0.00
10 73 33	marquees					0.00
10 74 00	exterior clocks					0.00
10 74 23	cupolas					0.00
10 74 33	weathervanes					0.00
10 74 43	below-grade egress assemblies					0.00
10 74 46	window wells	m/l	ea	1	380	380.00
10 75 00	flagpoles					0.00
10 80 00	other specialties					0.00
10 84 13	exterior gas lighting					0.00
						0.00
11 00 00	EQUIPMENT	9225.00				0.00
11 13 00	loading dock equipment					0.00
11 20 00	commercial equipment					0.00
11 24 19	vacuum cleaning systems		bid	1	3200	3200.00
11 30 00	residential equipment					0.00
11 31 13	residential kitchen appliances		lump	1	3500	3500.00
11 31 23	residential laundry appliances		lump	1	1500	1500.00
11 33 00	retractable stairs		ea	1	325	325.00
11 34 00	residential ceiling fans		ea	2	350	700.00
11 40 00	food service equipment					0.00
11 50 00	educational and scientific equipment					0.00
11 60 00	entertainment equipment					0.00
11 70 00	healthcare equipment					0.00
11 82 00	solid waste disposal equipment					0.00
11 91 00	religious equipment					0.00
11 91 13	baptistries					0.00
11 92 00	agricultural equipment					0.00
11 93 00	horticultural equipment					0.00
11 95 00	arts and crafts equipment					0.00
						0.00
12 00 00	FURNISHINGS	24528.00				0.00
12 10 00	art					0.00
12 20 00	window treatments		lump	1	2500	2500.00
12 30 00	casework - cabinets - hardware		bid	1	14464	14464.00
12 31 00	manufactured metal casework					0.00
12 32 13	manufactured wood-veneer-faced casework					0.00
12 32 16	manufactured plastic-laminate-clad casework					0.00
12 35 00	specialty casework					0.00
12 36 13	concrete countertops					0.00
12 36 16	metal countertops					0.00
12 36 19	wood countertops					0.00
12 36 23	plastic countertops		bid	1	4764	4764.00
12 36 23.13	plastic-laminate-clad countertops					0.00
12 36 40	stone countertops					0.00
12 36 53	labratory countertops					0.00
12 36 61	simulated stone countertops					0.00
12 40 00	furnishings and accessories					0.00
12 44 16	shower curtains					0.00
12 46 19	clocks					0.00
12 46 33	waste receptacles					0.00
12 48 00	rugs and mats					0.00
12 50 00	furniture					0.00
12 60 00	multiple seating					0.00
12 90 00	other furnishings	built-in bfast	ea	1	2800	2800.00
12 92 00	interior planters and artificial plants					0.00
12 93 13	bicycle racks					0.00
12 93 23	trash and litter receptors					0.00
12 93 33	manufactured planters					0.00
12 93 43	site seating and tables					0.00
						0.00
13 00 00	SPECIAL CONSTRUCTION	2892.00				0.00
13 11 00	swimming pools					0.00
13 12 13	exterior fountains					0.00
13 12 23	interior fountains					0.00
13 17 00	tubs and pools					0.00
13 19 00	kennels and animal shelters	m/l	lump	1	650	650.00
13 20 00	special purpose rooms					0.00
13 21 00	controlled environment rooms					0.00
13 24 16	saunas					0.00
13 27 53	security vaults					0.00
13 30 00	special structures					0.00
13 31 00	fabric structures					0.00
13 32 00	space frames					0.00
13 34 00	fabricated engineered structures					0.00
13 34 13.13	greenhouses					0.00
13 34 13.16	solariums					0.00
13 34 13.19	swimming pool enclosures					0.00
13 34 13.23	sunrooms					0.00
13 34 13.26	conservatories					0.00
13 34 18	post frame building systems					0.00
13 34 19	metal building systems					0.00
13 34 23	fabricated structures	gazebo	ea	1	2242	2242.00
13 36 00	towers					0.00
13 40 00	intergrated construction					0.00
13 50 00	special instrumentation					0.00
						0.00
14 00 00	CONVEYING EQUIPMENT	5722.00				0.00
14 10 00	dumbwaiters	m/l	ea	1	5500	5500.00
14 20 00	elevators					0.00
14 40 00	lifts					0.00
14 42 00	wheelchair lifts					0.00
14 70 00	turntables					0.00
14 80 00	scaffolding					0.00
14 90 00	other conveying equipment					0.00
14 91 00	facility chutes	laundry chute	ea	1	222	222.00
						0.00
21 00 00	FIRE SUPPRESSION	0.00				0.00
21 07 00	fire suppression systems insulation					0.00
21 10 00	water-based fire suppression systems					0.00
21 12 00	fire suppression standpipes					0.00
21 13 00	fire suppression sprinkler system					0.00
21 20 00	fire extinguishing systems					0.00
21 30 00	fire pumps					0.00
21 40 00	fire suppression water storage					0.00
						0.00
22 00 00	PLUMBING	13150.00				0.00
22 07 00	plumbing insulation		bid	1	500	500.00
22 09 00	instrumentation and control for plumbing					0.00
22 10 00	plumbing piping	pipe - equip	bid	1	8450	8450.00
22 30 00	plumbing equipment					0.00
22 40 00	plumbing fixtures		lump	1	4200	4200.00
22 47 00	drinking fountains and water coolers					0.00
22 50 00	pool and fountain plumbing systems					0.00
						0.00
23 00 00	HVAC	9007.00				0.00
23 07 00	hvac insulation		bid	1	220	220.00
23 10 00	facility fuel systems					0.00
23 20 00	hvac piping and pumps					0.00
23 21 13	hydronic piping					0.00
23 30 00	hvac air distribution					0.00
23 38 13	commercial kitchen hoods					0.00
23 40 00	hvac air cleaning devices					0.00
23 50 00	central heating equipment					0.00
23 60 00	central cooling equipment					0.00
23 70 00	central hvac equipment		bid	1	8787	8787.00
23 80 00	decentralized hvac equipment					0.00
						0.00
25 00 00	INTEGRATED AUTOMATION	0.00				0.00
25 10 00	integrated automation network equipment					0.00
25 30 00	integrated auto instrumentation and terminal devices					0.00
25 50 00	integrated automation facility controls					0.00
						0.00
26 00 00	ELECTRICAL	14804.00				0.00
26 09 13	electrical power monitoring					0.00
26 09 16	electrical controls & relays					0.00
26 09 17	programmable controllers					0.00
26 09 23	lighting control devices					0.00
26 09 33	central dimming controls					0.00
26 09 43	network lighting controls					0.00
26 09 61	theatrical lighting controls					0.00
26 10 00	med voltage electrical distribution & service		bid	1	12454	12454.00
26 20 00	low voltage electrical transmission	included				0.00
26 30 00	facility electrical power generation and storing equip					0.00
26 40 00	electrical and cathodic protection					0.00
26 51 00	interior lighting		lump	1	2000	2000.00
26 52 00	emergency lighting					0.00
26 53 00	exit signs					0.00
26 54 00	classified location lighting					0.00
26 55 00	special purpose lighting					0.00
26 56 00	exterior lighting		lump	1	350	350.00
						0.00
27 00 00	COMMUNICATIONS	1800.00				0.00
27 10 00	structured cabling		bid	1	1800	1800.00
27 20 00	data communications					0.00
27 30 00	voice communications					0.00
27 40 00	audio-video communications					0.00
27 50 00	distributed communications monitoring systems					0.00
27 60 00	wireless transceivers					0.00
						0.00
28 00 00	ELECTRONIC SAFETY AND SECURITY	0.00				0.00
28 10 00	electronic access control and intrusion detection					0.00
28 20 00	electronic surveillance					0.00
28 30 00	electronic detection and alarm					0.00
28 40 00	electronic monitoring and control					0.00
						0.00
31 00 00	EARTHWORK	12915.00				0.00
31 09 00	geotechnical instrumentation and monitoring		trips	2	125	250.00
31 11 00	clearing and grubbing	equip + man	hours	16	115	1840.00
31 12 00	selective clearing					0.00
31 13 00	selective tree and shrub removal and trimming					0.00
31 14 00	earth stripping and stockpiling	incl w grubbing				0.00
31 22 13	rough grading	blade	hours	8	75	600.00
31 22 16	fine grading	blade	hours	12	75	900.00
31 22 19	finish grading	incl landscabe bid				0.00
31 23 13	subgrade preparation					0.00
31 23 16	excavation	hoe	hours	10	75	750.00
31 23 19	dewatering					0.00
31 23 23	fill					0.00
31 23 33	trenching and backfilling	water-sewer-cable-phone m/l	bid	1	1450	1450.00
31 30 00	earthwork methods					0.00
31 31 00	soil treatment					0.00
31 32 00	soil stabilization					0.00
31 33 00	rock stabilization					0.00
31 34 00	soil reinforcement					0.00
31 35 00	slope protection		bid	1	3275	3275.00
31 36 00	gabions					0.00
31 37 00	riprap					0.00
31 40 00	shoring and underpinning					0.00
31 50 00	excavation support and protection					0.00
31 51 00	anchor tiebacks					0.00
31 52 00	cofferdams					0.00
31 54 00	ground freezing					0.00
31 60 00	special foundations and load-bearing elements					0.00
31 62 00	driven piles					0.00
31 63 00	bored piles					0.00
31 68 00	foundation anchors		bid	1	3850	3850.00
						0.00
32 00 00	EXTERIOR IMPROVEMENTS	45233.00				0.00
32 11 16	subbase courses					0.00
32 11 23	aggregate base courses					0.00
32 11 26	asphaltic base courses					0.00
32 11 36	concrete base courses					0.00
32 12 13	asphalt paving	quote w base courses	bid	1	3850	3850.00
32 12 33	flexible paving surface treatments					0.00
32 12 36	seal coats					0.00
32 13 13	concrete paving					0.00
32 13 16	decorative concrete paving		sf	320	18	5760.00
32 15 00	aggregate surfacing	landscaping	bid	1	886	886.00
32 16 13	curbs and gutters					0.00
32 16 23	sidewalks		sf	320	6	1920.00
32 16 33	driveways		sf	400	4.5	1800.00
32 17 13	parking bumpers					0.00
32 17 16	speed bumps					0.00
32 17 23	pavement markings					0.00
32 18 00	athletic and recreational surfacing					0.00
32 30 00	site improvements					0.00
32 31 00	fences and gates		bid	1	12987	12987.00
32 32 00	retaining walls	incl drainage	sf	120	32	3840.00
32 34 00	fabricated bridges					0.00
32 39 00	manufactured site specialties	benches	ea	2	320	640.00
32 70 00	wetlands					0.00
32 71 00	constructed wetlands					0.00
32 72 00	wetlands restoration					0.00
32 80 00	irrigation		bid	1	5500	5500.00
32 90 00	planting		bid	1	4850	4850.00
32 92 00	turf and grasses		bid	1	3200	3200.00
						0.00
33 00 00	UTILITIES	11275.00				0.00
33 10 00	water utilities	connection fees	ea	1	6500	6500.00
33 20 00	wells					0.00
33 30 00	sanitary sewerage utilities	connection fees	ea	1	2200	2200.00
33 36 00	utility septic tanks & fields					0.00
33 40 00	storm drainage utilities		bid	1	2250	2250.00
33 50 00	fuel distribution utilities					0.00
33 60 00	hydronic and steam energy utilities					0.00
33 70 00	electric utilities	connection fees	ea	1	325	325.00
33 80 00	communications utilities					0.00
						0.00
35 00 00	WATERWAY AND MARINE CONSTRUCTION	0.00				0.00
35 21 00	shoreline protection					0.00
35 42 00	waterway bank protection					0.00
35 51 00	floating construction					0.00
35 52 00	offshore platform construction					0.00
						0.00
	TOTALS:	417331.85				417331.85

## onePageSchedule
			Project:		Sampleclient New Residence					Job No:			5001					Date:
			Project Objective:

Objectives				Major Tasks			Projected Completion Date:					Owner
				March				April				May				June				July				August				September				October				November				Client	Dean	Tony	Thom

			Site	Pre Construction
				Site Prep
				Excavation
				Foundation
				Utilities & drainage
				Backfill & grading
				Concrete slabs exterior
				Rockery & Landscaping
			Rough	Framing
				Roofing
				Plumbing rough
				Electrical rough
				Fireplace
				Masonry & siding
				Concrete slabs interior
				HVAC & infloor
				Insulation
				Exterior & garage doors
			Finish	Drywall
				Decks & porches
				Painting & wallpaper
				Electric finish
				Special Projects
				Doors & trim
				Tile work
				Cabinets & built-ins
				Counter tops
				Floorings
				Plumbing finish
				Appliances & equipment
			Wrap	Punch list
				Remove Temp BMPs
				Cleanup / Tasks

				Budget:
		Objectives				Costs		Err:520

				Summary				Actual:
				$-

				31		31